## Sheet1
Mark Jervelund thesis plan |  | Date Start | Date end |  | Anything before this has been unstructured study, a lot of finding materials and such. | Mile stone
November | Week 45 | November 2, 2020 | November 8, 2020 | Structured study 8 weeks | Study jepsen test
| Week 46 | November 9, 2020 | November 15, 2020
| Week 47 | November 16, 2020 | November 22, 2020 |  | Finish study on Jepsen test
| Week 48 | November 23, 2020 | November 29, 2020
December | Week 49 | November 30, 2020 | December 6, 2020 |  | Study Service Fabric | Initial draft on related work as well as draft on draft on what exeriments should be done
| Week 50 | December 7, 2020 | December 13, 2020
| Week 51 | December 14, 2020 | December 20, 2020 |  | Chrismas break
| Week 52 | December 21, 2020 | December 27, 2020
| Week 53 | December 28, 2020 | January 3, 2021 |  | Finish Study Service Fabric
January | week 01 | January 4, 2021 | January 10, 2021
| Week 02 | January 11, 2021 | January 17, 2021 | Experiment 10 weeks | designing the experiment
| Week 03 | January 18, 2021 | January 24, 2021
| Week 04 | January 25, 2021 | January 31, 2021 |  | designing the experiment
Febuary | Week 05 | February 1, 2021 | February 7, 2021
| Week 06 | February 8, 2021 | February 14, 2021 |  | Excecute the exeriment
| Week 07 | February 15, 2021 | February 21, 2021
| Week 08 | February 22, 2021 | February 28, 2021 |  | Analyse the experiment
March | Week 09 | March 1, 2021 | March 7, 2021
| Week 10 | March 8, 2021 | March 14, 2021 |  | discover what the findings from the exeriment is
| Week 11 | March 15, 2021 | March 21, 2021
| Week 12 | March 22, 2021 | March 28, 2021 | Thesis writing 10 weeks | Running additional experiments if needed Full on write mode
| Week 13 | March 29, 2021 | April 4, 2021
April | Week 14 | April 5, 2021 | April 11, 2021 |  | Full on write mode
| Week 15 | April 12, 2021 | April 18, 2021
| Week 16 | April 19, 2021 | April 25, 2021 |  | Full on write mode
| Week 17 | April 26, 2021 | May 2, 2021
May | Week 18 | May 3, 2021 | May 9, 2021 |  | Full on write mode Send out thesis for feedback
| Week 19 | May 10, 2021 | May 16, 2021
| Week 20 | May 17, 2021 | May 23, 2021 |  | Correction
| Week 21 | May 24, 2021 | May 30, 2021
| Week 22 | May 31, 2021 | June 6, 2021 | goal | Hand in
June | Week 23 | June 7, 2021 | June 13, 2021
| Week 24 | June 14, 2021 | June 20, 2021
| Week 25 | June 21, 2021 | June 27, 2021
| Week 26 | June 28, 2021 | July 4, 2021
Week 27
Week 28
Week 29
Week 30
Week 31